## README
Field | Details
Document | Prophetic Destinations – Detailed Product & CMS Feature Specification
Purpose | Development-team handoff and AI-assisted implementation reference. Each feature is written so it can be converted into tickets/prompts without relying on the original proposal.
Project | Interactive Bible Prophecy Learning Mobile Application + Web Admin CMS
Project start | 1 October 2026
Target duration | 3 months: 2 months development + 1 month alpha/beta testing and launch
Primary users | Learner (mobile app); Prophetic Destinations Administrator/Editor (web CMS)
Core product principle | Do not reproduce a text-heavy Bible-study book/PDF on a phone. Convert approved content into a mobile-first visual learning journey. Use interaction only when it materially improves understanding.
Learning levels | Beginner, Intermediate, Advanced. A lesson can be assigned to one or more levels; individual blocks can also be level-targeted; selected blocks may have level-specific variants.
Bible decision | Include the full KJV Bible as a supporting app feature. Required verses still appear directly inside lessons; references should be structured and tappable into the Bible reader.
Offline decision | No explicit Download Lesson button. Opening a lesson should cache/download required content/assets in the background so the lesson can subsequently continue offline.
Account/privacy decision | No learner registration/login/profile in initial scope. Progress is stored locally and is device-specific.
CMS principle | Structured reusable components, not a generic drag-anything-anywhere no-code page builder. Standard lessons should be publishable without app development.
Scope boundary | A new custom interactive mechanism, complex animation, specialized visualization or major new module outside supported components requires separate estimation/approval.
Content authority | Client supplies/approves theology, educational content, historical interpretations/references and proprietary artwork. Development team must not silently change theological meaning.
Source basis | Accepted project proposal + lesson/CMS decisions developed from Revelation 1, Revelation 5 and introductory 1,260-day study discussions.
How to use | Filter Feature Register by Epic, Surface, Priority, Milestone or Status. Use Acceptance Criteria and AI Prompt Notes as the starting point for implementation prompts/tickets.
Priority legend | P0 = required for launch / contractual core; P1 = important included capability; P2 = useful enhancement if time permits within agreed implementation.
Status legend | Confirmed = agreed; Design Detail = implementation detail derived from agreed scope; Scope Guard = explicit boundary/out-of-scope warning.

## Feature Register
ID | Epic | Surface | Feature | User / Actor | Requirement / Behavior | Level Behavior | Offline / Persistence | Admin / Data Needs | Acceptance Criteria | Priority | Milestone | Status | AI Prompt Notes | Source
APP-001 | Onboarding & Levels | Mobile | First-launch entry | Learner | Provide a simple first-launch path into the app without account creation. Offer optional assessment or direct level selection. |  | Persist assessment/selected level locally. |  | User can reach a lesson without registering or logging in. | P0 | M1 | Confirmed | Implement first-launch flow with two primary actions: Take Assessment and Choose Level. No auth dependency. | Proposal
APP-002 | Onboarding & Levels | Mobile | Optional initial assessment | Learner | Short multiple-choice assessment recommends Beginner, Intermediate or Advanced based on configured scoring. | Recommendation does not restrict level choice. | Store completion/result locally. | Assessment questions, options, correct answers, score thresholds. | User can complete or skip assessment; completion yields one recommended level. | P0 | M1 | Confirmed |  | Proposal
APP-003 | Onboarding & Levels | Mobile | Skip assessment | Learner | Allow learner to skip assessment and choose a level directly. |  | Persist selected level locally. |  | Skip never blocks app usage. | P0 | M1 | Confirmed |  | Proposal
APP-004 | Onboarding & Levels | Mobile | Manual learning-level selection | Learner | Allow choosing Beginner, Intermediate or Advanced regardless of assessment recommendation. |  | Persist selected level. |  | Changing level changes visible lesson/block content according to CMS rules. | P0 | M1 | Confirmed |  | Proposal
APP-005 | Onboarding & Levels | Mobile | Change / retake level | Learner | More area provides Learning Level and Retake Assessment. |  | Update local state without deleting progress. |  | Existing progress remains intact when level changes. | P1 | M4 | Confirmed |  | Proposal
APP-010 | Navigation | Mobile | Primary navigation | Learner | Provide app areas similar to Home, Learn, Progress and More; final labels may be refined. |  | Navigation works offline for cached/local areas. |  | All primary areas reachable consistently. | P0 | M1 | Confirmed |  | Proposal
APP-011 | Home | Mobile | Continue Learning | Learner | Show resumable lesson when unfinished progress exists. |  | Resume position stored locally. |  | Tapping resumes the correct lesson near last saved position. | P0 | M4 | Confirmed |  | Proposal
APP-012 | Home | Mobile | Current progress summary | Learner | Show concise overall learning progress. |  | Derived from local progress. |  | Summary updates after lesson/quiz completion. | P1 | M4 | Confirmed |  | Proposal
APP-013 | Home | Mobile | Daniel entry | Learner | Provide direct entry to Daniel course/book lessons filtered for current level. | Respect lesson availability. | Use cached metadata when offline. |  | Only eligible/published lessons are shown. | P0 | M1 | Confirmed |  | Proposal
APP-014 | Home | Mobile | Revelation entry | Learner | Provide direct entry to Revelation course/book lessons filtered for current level. | Respect lesson availability. | Use cached metadata when offline. |  | Only eligible/published lessons are shown. | P0 | M1 | Confirmed |  | Proposal
APP-015 | Learn | Mobile | Level-based lesson catalog | Learner | Browse Beginner, Intermediate and Advanced and lessons within each level. | Lesson can belong to one or more levels. | Cached catalog available after sync. |  | Published lessons appear in configured order. | P0 | M1 | Confirmed |  | Proposal
LESS-001 | Lesson Engine | Mobile | Structured lesson renderer | Learner | Render lessons as ordered reusable content blocks from CMS, optimized for portrait mobile screens. | Filter blocks/variants by active level. | Lesson payload/assets cache after opening. | Ordered block JSON/content model. | A CMS-authored lesson renders in configured order without hardcoding lesson-specific screens. | P0 | M2 | Confirmed | Build registry-driven lesson renderer: block.type -> renderer component. Unknown block types fail gracefully and are logged. | Proposal
LESS-002 | Lesson Engine | Mobile | Level-filtered blocks | Learner | Show only blocks whose level visibility includes learner current level. | Explicit B/I/A booleans or equivalent array. | Filtering works from cached lesson payload. | Block visibility metadata. | Switching level results in correct block set. | P0 | M2 | Confirmed |  | Proposal
LESS-003 | Lesson Engine | Mobile | Level-specific block variants | Learner | For supported blocks, allow same conceptual section to provide different Beginner/Intermediate/Advanced content. | Use exact matching variant; define CMS fallback behavior. | Variants cache with lesson. | Variant content per level. | Preview and mobile render same selected variant. | P1 | M2 | Design Detail |  | Proposal
LESS-004 | Lesson Engine | Mobile | Save reading position | Learner | Persist current position within unfinished lesson at reasonable checkpoints. |  | Local device only. |  | Reopening via Continue Learning returns near prior position. | P0 | M4 | Confirmed |  | Proposal
LESS-005 | Lesson Engine | Mobile | Mark lesson complete | Learner | Mark completion when learner reaches defined completion condition/end. |  | Local device only. |  | Completed state appears in Progress and lesson list. | P0 | M4 | Confirmed |  | Proposal
LESS-006 | Lesson Engine | Mobile | Mobile-first presentation | Learner | Prefer scrolling, cards, full/near-full-width visuals, bottom sheets and touch interactions; avoid desktop-style wide layouts. |  |  |  | No horizontal overflow on supported phone sizes; comparison/table content adapts to cards/stacking. | P0 | M2 | Design Detail |  | Proposal
LESS-007 | Lesson Engine | Mobile | Direct presentation of Scripture/explanation | Learner | Do not hide ordinary Bible verses/explanations behind unnecessary tap-to-reveal interactions. |  |  |  | Core instructional content is visible in normal reading flow unless interaction adds learning value. | P0 | M2 | Confirmed |  | Proposal
BLK-001 | Lesson Components | Mobile + CMS | Rich Text | Learner / Admin | Short explanatory content with constrained formatting: headings, paragraphs, bold/italic, lists and references. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-002 | Lesson Components | Mobile + CMS | Section Intro / Heading | Learner / Admin | Major lesson transition with title, optional subtitle and visual treatment. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-003 | Lesson Components | Mobile + CMS | Callout / Key Idea | Learner / Admin | Emphasize Remember, Key Idea, Prophecy Principle or similar short content. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-004 | Lesson Components | Mobile + CMS | Scripture Passage | Learner / Admin | Display selected KJV verse range inline with structured reference and Open in Bible action. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-005 | Lesson Components | Mobile + CMS | Scripture Connection | Learner / Admin | Show a configured sequence/comparison of related passages with labels and tappable references. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-006 | Lesson Components | Mobile + CMS | Image / Illustration | Learner / Admin | Display image with caption, alt text and source/rights metadata where applicable. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-007 | Lesson Components | Mobile + CMS | Interactive Image / Hotspots | Learner / Admin | Display an image with configured tappable hotspots; each hotspot opens approved label/explanation/Scripture in a mobile sheet/panel. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-008 | Lesson Components | Mobile + CMS | Symbol Study | Learner / Admin | Present symbol, primary passage, biblical definition/meaning, explanation and related references. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-009 | Lesson Components | Mobile + CMS | Word Study | Learner / Admin | Present English word, original-language word, transliteration, optional Strong number, curated definition, verse and references. No full concordance engine. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-010 | Lesson Components | Mobile + CMS | Prophecy Equivalence | Learner / Admin | Visually connect multiple prophetic expressions to a common concept/time period, e.g. 42 months ↔ 1,260 days ↔ time/times/half a time. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-011 | Lesson Components | Mobile + CMS | Prophecy Calculation | Learner / Admin | Present configured step-by-step arithmetic/relationship rows such as 42 × 30 = 1,260. Presentation only; not a general formula engine. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-012 | Lesson Components | Mobile + CMS | Prophecy Comparison | Learner / Admin | Compare characteristics/entities/passages. On phones, adapt wide matrix into readable cards/sections. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-013 | Lesson Components | Mobile + CMS | Timeline | Learner / Admin | Display ordered events/periods with title, date/period, description, Scripture and optional image. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-014 | Lesson Components | Mobile + CMS | Map / Diagram | Learner / Admin | Display map/diagram with optional markers/hotspots using predefined interaction. Not a general GIS/map editor. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-015 | Lesson Components | Mobile + CMS | Narrative Scene | Learner / Admin | Create visual story transition using background/illustration, concise narrative text, Scripture and predetermined effects. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-016 | Lesson Components | Mobile + CMS | Media / Animation Asset | Learner / Admin | Render supported video/animation/Lottie-type asset supplied/approved for lesson. CMS integrates asset; does not create animations. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-017 | Lesson Components | Mobile + CMS | Explore Deeper | Learner / Admin | Optional/deeper-study container or card that can hold supported deeper content and be targeted to levels. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-018 | Lesson Components | Mobile + CMS | Reflection / Study Activity | Learner / Admin | Display configured Reflect/Compare/Find/Study/Read/Personal Application instruction with references. No in-app journal required. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-019 | Lesson Components | Mobile + CMS | Guided Discovery Question | Learner / Admin | Ask a configured study question and direct learner to passage/explanation; use sparingly, not as needless tap-to-reveal. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P2 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BLK-020 | Lesson Components | Mobile + CMS | Historical Evidence | Learner / Admin | Present period/date, explanation, source/reference, optional image/map; depth can vary by level. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-021 | Lesson Components | Mobile + CMS | Lesson Summary | Learner / Admin | Present configured key ideas, key Scripture, prophecy takeaway and spiritual/application takeaway. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P0 | M2/M3 | Confirmed |  | Proposal + lesson-derived CMS design
BLK-022 | Lesson Components | Mobile + CMS | Continue Exploring | Learner / Admin | Manual links to next/related lessons. This is curated linking, not AI/intelligent recommendation. | Block supports B/I/A visibility; selected blocks may support variants. | Included in lesson cache where applicable. | CMS editor for component fields. | Admin can configure component; mobile renders it correctly and responsively. | P1 | M2/M3 | Design Detail |  | Proposal + lesson-derived CMS design
BIB-001 | KJV Bible | Mobile | Full KJV Bible | Learner | Include complete KJV Bible as a supporting app feature. | Same Bible for all levels. | Bible text should be available offline with app/local data. | Canonical read-only KJV dataset. | Learner can navigate all 66 books and chapters without internet. | P0 | M4 | Confirmed | Use a normalized local Bible dataset. Keep canonical text read-only in CMS. | Post-proposal agreed decision
BIB-002 | KJV Bible | Mobile | Book/chapter navigation | Learner | Browse Bible by book and chapter; support verse display. |  | Offline. |  | Navigation is fast and usable on phone. | P0 | M4 | Confirmed |  | Proposal
BIB-003 | KJV Bible | Mobile | Open reference from lesson | Learner | Tapping a structured Scripture reference opens corresponding Bible location while preserving return path/lesson position. |  | Offline if Bible local. | Structured reference fields. | Back returns learner to prior lesson context. | P0 | M4 | Confirmed |  | Proposal
BIB-004 | KJV Bible | CMS | Scripture picker | Admin | Select book, chapter, start verse and end verse rather than typing references only. |  |  | Canonical Bible index. | CMS validates range and previews KJV text. | P0 | M3 | Design Detail |  | Proposal
BIB-005 | KJV Bible | CMS | Canonical Bible text protection | Admin | Ordinary lesson editors reference KJV but do not casually edit canonical Bible text. |  |  | Read-only/privileged dataset. | No standard lesson editing workflow can modify Bible text. | P1 | M3 | Design Detail |  | Proposal
BIB-006 | KJV Bible | Mobile | Basic Bible search | Learner | Provide simple keyword/reference search if achievable within implementation; advanced concordance is excluded. |  | Prefer local index/offline. |  | Search returns relevant KJV verses and opens selected result. | P2 | M4 | Design Detail |  | Proposal
QUIZ-001 | Quizzes | Mobile + CMS | End-of-lesson quiz | Learner / Admin | Quiz appears at lesson end; supports multiple-choice questions, feedback/explanations, final score and review/completion. | Questions may be level-targeted. | Quiz result stored locally. | Question, options, correct option, explanations, Scripture, level. | Correct scoring; result persists; learner can review according to product design. | P0 | M2/M3 | Confirmed |  | Proposal
QUIZ-002 | Quizzes | CMS | Question bank per lesson | Admin | Create/edit/delete/order quiz questions and answer options for a lesson. | Assign B/I/A visibility to question. |  |  | Published lesson delivers only eligible questions. | P0 | M3 | Confirmed |  | Proposal
QUIZ-003 | Quizzes | Mobile | Level-appropriate quiz | Learner | Use only questions enabled for current level; number of questions may differ by level. | B/I/A filtering. | Local result. |  | Beginner does not receive Advanced-only question. | P1 | M2/M3 | Design Detail |  | Proposal
PROG-001 | Progress | Mobile | Local progress model | Learner | Store selected level, assessment, started/completed lessons, current position, quiz completion/scores and overall progress locally. |  | Device-specific; no cloud sync. |  | Data survives normal app restart. | P0 | M4 | Confirmed |  | Proposal
PROG-002 | Progress | Mobile | Progress screen | Learner | Show lessons completed, lessons remaining, quiz scores and overall progress. |  | Derived locally. |  | Screen reflects latest local state. | P0 | M4 | Confirmed |  | Proposal
OFF-001 | Offline | Mobile | Automatic lesson caching | Learner | When lesson opens, automatically cache/download lesson content and required assets in background; no separate download action. |  | Persist cached lesson assets/content. | Lesson asset manifest/version. | After successful load, lesson can be reopened without network. | P0 | M4 | Confirmed |  | Proposal
OFF-002 | Offline | Mobile | Cache update/versioning | Learner | When online, detect published lesson version changes and refresh safely without corrupting local progress. |  | Maintain cache metadata. | Content version/published timestamp. | Updated lesson replaces stale content while preserving compatible progress. | P1 | M4 | Design Detail |  | Proposal
SHR-001 | Sharing | Mobile | Invite a Friend | Learner | Use native OS share sheet to share invitation/app link; app does not collect/store contacts. |  | No contact storage. | Configurable share text/store link. | Native share opens with configured message/link. | P0 | M4 | Confirmed |  | Proposal
CMS-001 | Admin CMS | CMS | Authentication & authorized admin access | Authorized Admin | Provide secure web CMS access for authorized Prophetic Destinations administrators. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-002 | Admin CMS | CMS | Dashboard | Admin | Show practical entry points/recent content; avoid analytics-heavy scope unless separately agreed. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P2 | M3 | Design Detail |  | Proposal + CMS design
CMS-003 | Admin CMS | CMS | Books / Courses | Admin | Create/edit/order course containers such as Daniel, Revelation and approved future courses. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-004 | Admin CMS | CMS | Modules / Series | Admin | Optional grouping of lessons into series/modules within a course. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-005 | Admin CMS | CMS | Lesson CRUD | Admin | Create, edit, duplicate, archive/delete and order lessons. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-006 | Admin CMS | CMS | Lesson metadata | Admin | Manage title, short title, subtitle, intro, cover image, estimated study time, course/module, order, available levels, status and related lesson links. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-007 | Admin CMS | CMS | Lesson builder | Admin | Add supported blocks, edit, duplicate, delete/hide and drag/reorder blocks. Not a free-form page designer. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-008 | Admin CMS | CMS | Block level visibility | Admin | For each block, explicitly select Beginner, Intermediate, Advanced or combinations. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-009 | Admin CMS | CMS | Level-specific variants | Admin | For supported blocks, optionally edit separate B/I/A content variants under one conceptual section. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-010 | Admin CMS | CMS | Level coverage view | Admin | Show at-a-glance matrix/list of which lesson sections appear at each level. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P2 | M3 | Design Detail |  | Proposal + CMS design
CMS-011 | Admin CMS | CMS | Preview by level | Admin | Preview lesson as Beginner, Intermediate or Advanced before publishing, using mobile-like presentation. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-012 | Admin CMS | CMS | Draft/review/published workflow | Admin | Support Draft, Ready for Review, Approved/Published and optional Archived state. Only published content reaches learners. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-013 | Admin CMS | CMS | Lesson ordering | Admin | Control lesson order within course/module and block order within lesson. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-014 | Admin CMS | CMS | Reusable content blocks | Admin | Create reusable study blocks for recurring content. Support linked reuse and independent duplication if practical. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-015 | Admin CMS | CMS | Media library | Admin | Upload/manage images, maps, diagrams, animation/video assets with title, alt text, source/rights, tags and usage metadata where practical. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-016 | Admin CMS | CMS | Image hotspot editor | Admin | Upload/select image, place hotspots, and configure label, explanation, Scripture/references and level visibility for each hotspot. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-017 | Admin CMS | CMS | Timeline editor | Admin | Create ordered timeline events with date/period, title, description, Scripture, optional image and level visibility. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-018 | Admin CMS | CMS | Historical evidence editor | Admin | Manage historical description, dates/periods, supporting references/sources and optional media. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-019 | Admin CMS | CMS | Quiz editor | Admin | Manage lesson quiz questions, answer options, correct answers, explanations, Scripture and level visibility. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-020 | Admin CMS | CMS | Summary editor | Admin | Manage lesson conclusion/review content. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P0 | M3 | Confirmed |  | Proposal + CMS design
CMS-021 | Admin CMS | CMS | Topic / tags | Admin | Tag lessons/blocks with recurring topics for organization and possible future related-study use. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P2 | M3 | Design Detail |  | Proposal + CMS design
CMS-022 | Admin CMS | CMS | Word study editor | Admin | Enter curated original-language study data; do not implement a full Strong concordance engine. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-023 | Admin CMS | CMS | Symbol study editor | Admin | Configure symbol, passage, biblical definition/meaning, explanation and related references. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-024 | Admin CMS | CMS | Prophecy equivalence editor | Admin | Configure central concept plus equivalent expressions/references and optional explanatory labels. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-025 | Admin CMS | CMS | Prophecy comparison editor | Admin | Configure comparison entities/passages, characteristics, supporting references and explanations. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-026 | Admin CMS | CMS | Calculation visual editor | Admin | Configure simple ordered calculation/relationship steps for prophecy math. No arbitrary scripting/formula engine. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-027 | Admin CMS | CMS | Related lesson links | Admin | Manually choose next/related lessons. Not intelligent recommendation. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-028 | Admin CMS | CMS | Duplicate lesson/section/block | Admin | Allow duplication to accelerate authoring similar lessons. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P1 | M3 | Design Detail |  | Proposal + CMS design
CMS-029 | Admin CMS | CMS | Revision history | Admin | Maintain basic saved revisions/restore if feasible; no Google-Docs-style collaboration. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P2 | M3 | Design Detail |  | Proposal + CMS design
CMS-030 | Admin CMS | CMS | Asset size awareness | Admin | Where practical show file size / warn about very large assets because lessons cache to device. | CMS itself is not level-filtered except preview; content carries level rules. |  | As described in requirement. | Admin can perform action and published mobile content reflects it correctly. | P2 | M3 | Design Detail |  | Proposal + CMS design
PUB-001 | Publishing | CMS + API | Published-content API | System | Expose only approved/published course, lesson and content payloads required by mobile app. | Include level metadata. | Mobile caches payloads. | Version, publish status, timestamps. | Draft content never appears in production learner API. | P0 | M3 | Confirmed |  | Proposal
PUB-002 | Publishing | CMS + Mobile | Content versioning | System | Provide stable IDs and version/update metadata for courses, lessons and assets. |  | Supports cache refresh. | Stable IDs, updated_at/version. | Mobile can determine whether cached content is stale. | P1 | M3/M4 | Design Detail |  | Proposal
MORE-001 | More / Legal | Mobile | About Prophetic Destinations | Learner | Display CMS/configured or bundled About content. |  | Available offline if bundled/cached. |  | Accessible from More. | P0 | M4 | Confirmed |  | Proposal
MORE-002 | More / Legal | Mobile | Privacy Policy | Learner | Provide appropriate privacy information required for app distribution/third-party services. |  | Cache or web fallback. |  | Accessible from More. | P0 | M4 | Confirmed |  | Proposal
MORE-003 | More / Legal | Mobile | Terms | Learner | Provide Terms information. |  | Cache or web fallback. |  | Accessible from More. | P0 | M4 | Confirmed |  | Proposal
NFR-001 | Non-Functional | Mobile | Responsive phone UX | Learner | Support intended iOS/Android phone layouts in portrait-first design; handle different common screen sizes safely. |  |  |  | No clipped critical content or unusable touch targets on supported devices. | P0 | M4 | Design Detail |  | Proposal
NFR-002 | Non-Functional | Mobile | Performance | Learner | Lazy-load/optimize media where appropriate; keep lesson scrolling responsive even with rich content. |  | Cache media. |  | No obvious UI blocking during ordinary lesson use. | P0 | M4 | Design Detail |  | Proposal
NFR-003 | Non-Functional | CMS | Content validation | Admin | Validate required fields, Scripture ranges, publish readiness and media references before publishing where practical. |  |  |  | Invalid required content cannot be published silently. | P1 | M3 | Design Detail |  | Proposal
NFR-004 | Non-Functional | CMS | Client content separation | Admin / Developer | Keep client-provided content/assets project-specific; generic code/components may be reusable but client artwork/content must not be reused in other projects. |  |  | Media/source metadata. | No client proprietary asset is exposed as a generic shared asset outside project. | P0 | M3 | Confirmed | Treat tenant/project asset namespace as isolated. | Contract/NDA decision
NFR-005 | Non-Functional | CMS | Theological content integrity | Admin / Developer | Do not silently rewrite theological interpretation. App/CMS must preserve client-approved content; adaptations require review. |  |  |  | Rendered content matches approved CMS content. | P0 | M3 | Confirmed |  | Proposal
Note on A1: OpenAI: Source basis: Prophetic Destinations project proposal provided by user, plus subsequent agreed product/CMS decisions in this conversation.

## CMS Components
Component | Purpose | CMS Fields / Configuration | Mobile Rendering | Level Support | Reuse / Notes | Scope Guard
Rich Text | Short explanatory content with constrained formatting: headings, paragraphs, bold/italic, lists and references. | Body; constrained formatting; optional references | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Section Intro / Heading | Major lesson transition with title, optional subtitle and visual treatment. | Title; subtitle; optional visual | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Callout / Key Idea | Emphasize Remember, Key Idea, Prophecy Principle or similar short content. | Callout type; title; body | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Scripture Passage | Display selected KJV verse range inline with structured reference and Open in Bible action. | Book; chapter; start verse; end verse; display mode | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Scripture Connection | Show a configured sequence/comparison of related passages with labels and tappable references. | Title; ordered connections; label; Scripture; explanation; display style | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Image / Illustration | Display image with caption, alt text and source/rights metadata where applicable. | Media asset; caption; alt text; source/rights | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Interactive Image / Hotspots | Display an image with configured tappable hotspots; each hotspot opens approved label/explanation/Scripture in a mobile sheet/panel. | Image; hotspot coordinates; label; explanation; Scripture; related references | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Symbol Study | Present symbol, primary passage, biblical definition/meaning, explanation and related references. | Symbol; image/icon; primary verse; meaning; definition verse; explanation; references | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Word Study | Present English word, original-language word, transliteration, optional Strong number, curated definition, verse and references. No full concordance engine. | English word; original word; transliteration; optional Strong number; curated definition; verse; references | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Prophecy Equivalence | Visually connect multiple prophetic expressions to a common concept/time period, e.g. 42 months ↔ 1,260 days ↔ time/times/half a time. | Central concept; equivalent items; Scripture references; labels; optional calculation | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Prophecy Calculation | Present configured step-by-step arithmetic/relationship rows such as 42 × 30 = 1,260. Presentation only; not a general formula engine. | Title; ordered steps; value; operator/explanation; result | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Prophecy Comparison | Compare characteristics/entities/passages. On phones, adapt wide matrix into readable cards/sections. | Entities/passages; characteristics; supporting references; explanation | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Timeline | Display ordered events/periods with title, date/period, description, Scripture and optional image. | Title; ordered events; date/period; description; Scripture; optional image | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Map / Diagram | Display map/diagram with optional markers/hotspots using predefined interaction. Not a general GIS/map editor. | Map/diagram asset; optional markers/hotspots; labels; explanations | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Narrative Scene | Create visual story transition using background/illustration, concise narrative text, Scripture and predetermined effects. | Title; visual; concise narrative; Scripture; predefined transition/effect | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Media / Animation Asset | Render supported video/animation/Lottie-type asset supplied/approved for lesson. CMS integrates asset; does not create animations. | Asset; media type; caption; poster/thumbnail; accessibility text | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Explore Deeper | Optional/deeper-study container or card that can hold supported deeper content and be targeted to levels. | Title; intro; supported nested/linked study content | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Reflection / Study Activity | Display configured Reflect/Compare/Find/Study/Read/Personal Application instruction with references. No in-app journal required. | Activity type; instruction; Scripture references | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Guided Discovery Question | Ask a configured study question and direct learner to passage/explanation; use sparingly, not as needless tap-to-reveal. | Question; Scripture; explanation; optional response interaction | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Historical Evidence | Present period/date, explanation, source/reference, optional image/map; depth can vary by level. | Title; date/period; explanation; source/reference; optional media | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Lesson Summary | Present configured key ideas, key Scripture, prophecy takeaway and spiritual/application takeaway. | Key ideas; key Scripture; prophecy takeaway; spiritual/application takeaway | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Continue Exploring | Manual links to next/related lessons. This is curated linking, not AI/intelligent recommendation. | Title; manually selected next/related lesson links | Responsive component renderer appropriate to the component; see Feature Register. | B/I/A visibility; selected components may have level variants. | Reusable structured block. | No arbitrary scripting or new custom mechanism; specialized interactions may require separate scope.
Note on A1: OpenAI: Source basis: Prophetic Destinations project proposal provided by user, plus subsequent agreed product/CMS decisions in this conversation.

## Data Model
Entity | Key Fields | Relationships | Rules / Notes
Course | id, title, slug, description, cover_asset_id, sort_order, status | has many Modules/Lessons | Stable IDs; only published course metadata sent to production app.
Module | id, course_id, title, description, sort_order, status | belongs Course; has many Lessons | Optional grouping layer.
Lesson | id, course_id/module_id, title, short_title, subtitle, intro, cover_asset_id, estimated_minutes, level flags, sort_order, status, version | has many LessonBlocks; Quiz; related lessons | Can be available to any combination of B/I/A.
LessonBlock | id, lesson_id, type, sort_order, level flags, variant_mode, payload_json, status | belongs Lesson; may reference Assets/Scriptures | Renderer driven by type. Payload validated against type schema.
BlockVariant | id, block_id, level, payload_json | belongs LessonBlock | Optional; only for supported block types. Define fallback explicitly.
ScriptureReference | id, book_id, chapter, start_verse, end_verse, display_mode | referenced by blocks/questions | Validate range against KJV dataset.
BibleBook | id, testament, canonical_order, name, abbreviation | has Chapters/Verses | Canonical/read-only ordinary CMS.
BibleVerse | book_id, chapter, verse, text | belongs BibleBook | KJV canonical dataset; available offline.
MediaAsset | id, type, file/url, title, alt_text, caption, source, rights_notes, size, tags | referenced by blocks | Project-specific asset namespace; optimize derivatives as needed.
Hotspot | id, block_id, x_pct, y_pct, label, explanation, level flags | belongs InteractiveImage block; references Scriptures | Use normalized percentage coordinates for responsive placement.
TimelineEvent | id, block_id, sort_order, date_or_period, title, description, level flags | belongs Timeline block | date_or_period is display text; not always Gregorian date.
HistoricalEvidence | id/block payload, title, period, description, source, references | belongs block/lesson | Client-approved content.
Quiz | id, lesson_id, title, pass_rule(optional) | has Questions | Quiz at end of lesson.
QuizQuestion | id, quiz_id, prompt, explanation, level flags, sort_order | has Options; references Scripture | Multiple choice in base scope.
QuizOption | id, question_id, text, is_correct, feedback | belongs Question | At least one correct option; base UX can assume single-correct unless explicitly expanded.
Assessment | id, title, status | has AssessmentQuestions/thresholds | Optional initial assessment.
AssessmentThreshold | level, min_score, max_score | belongs Assessment | Non-overlapping complete scoring bands.
LocalProgress | selected_level, assessment_result, lesson states, reading positions, quiz results | device-local only | No account/cloud sync in initial scope.
RelatedLesson | source_lesson_id, target_lesson_id, label, sort_order, level flags | Lesson-to-Lesson | Manual curation; not AI recommendation.
ReusableBlock | id, name, block_type, payload, level defaults, version | inserted/linked into lessons | If linked reuse is implemented, changes must be deliberate and previewable.

## User Flows
Flow ID | Actor | Flow | Steps | Success / Edge Cases
FLOW-01 | Learner | First launch | Open app → choose Take Assessment or Choose Level → assessment recommends level OR user selects level → Home | No login. Assessment skippable. Recommendation never locks user.
FLOW-02 | Learner | Start lesson | Home/Learn → choose course → choose eligible published lesson → lesson opens → content/assets cache → progress marked started | If offline and not previously cached, show clear unavailable/connectivity state; never lose existing progress.
FLOW-03 | Learner | Resume lesson | Home → Continue Learning → open unfinished lesson → restore near saved position | If lesson content updated, preserve compatible progress and resume safely.
FLOW-04 | Learner | Open Scripture | Tap lesson Scripture reference → open KJV Bible at passage → read/navigate → Back to Lesson | Return preserves lesson position.
FLOW-05 | Learner | Interactive image | View image → tap hotspot → open bottom sheet/panel → read explanation/Scripture → optionally open Bible → close/continue | Hotspots usable on small screens and accessible; no accidental navigation.
FLOW-06 | Learner | Complete quiz | Reach lesson end → start quiz → answer questions → feedback/explanation → final score → completion/review | Only questions eligible for current level. Result stored locally.
FLOW-07 | Learner | Offline continuation | Open lesson while online and allow load to complete → later open without network → continue lesson/quiz → progress saves locally | No explicit Download button. Missing uncached external assets fail gracefully.
FLOW-08 | Admin | Create lesson | CMS login → create lesson metadata → choose course/module + levels → add/reorder blocks → configure block level rules → add quiz/summary → preview each level → submit review/publish | Only supported block types; validation before publish.
FLOW-09 | Admin | Create interactive image | Choose block → select/upload image → add hotspot positions → enter label/explanation/Scripture/levels → preview on mobile frame → save/publish | Coordinates remain correct responsively.
FLOW-10 | Admin | Publish update | Edit draft → preview B/I/A → review/approve → publish → production API version changes → mobile refreshes when online | Draft never visible to learners.

## Acceptance Tests
Test ID | Area | Scenario | Precondition | Steps | Expected Result | Priority
AT-001 | Levels | Assessment can be skipped | Fresh install | Launch → Skip/Choose Level → select Intermediate | Home opens; Intermediate stored; no account requested. | P0
AT-002 | Levels | Recommendation does not restrict | Assessment configured | Complete with Beginner-range score → choose Advanced | Recommendation shows Beginner; user can still select Advanced. | P0
AT-003 | Lesson | Block level filtering | Lesson has B-only, I/A, and all-level blocks | Preview/open as each level | Each level sees exactly eligible blocks in configured order. | P0
AT-004 | Lesson | Level variant | Block has distinct B/I/A variants | Open lesson in each level | Correct variant renders; no content leakage from other levels. | P1
AT-005 | Bible | Structured reference opens Bible | Lesson contains Rev 5:1-4 | Tap reference | Bible opens Revelation 5 at target verses; Back returns to same lesson context. | P0
AT-006 | Offline | Lesson works after caching | Lesson loaded fully online | Disable network → reopen lesson | Text and required cached assets render; progress works. | P0
AT-007 | Progress | Resume position | Start long lesson | Scroll midway → exit app → reopen Continue Learning | Lesson resumes near saved location. | P0
AT-008 | Quiz | Level question filtering | Quiz contains B, I, A questions | Take quiz as Beginner | Advanced-only questions do not appear; score persists. | P0
AT-009 | CMS | Draft isolation | Lesson status Draft | Sync production app | Draft lesson is absent from learner catalog/API. | P0
AT-010 | CMS | Publish content | Valid reviewed lesson | Publish → refresh mobile online | Lesson appears with correct order, levels and blocks. | P0
AT-011 | Hotspots | Responsive hotspot placement | Interactive image configured | Preview/open on small and large supported phones | Hotspots remain aligned to intended image locations. | P0
AT-012 | CMS | Scripture validation | KJV dataset loaded | Select invalid verse range | CMS rejects invalid range and prevents bad reference from publishing. | P1
AT-013 | Sharing | Native share | App installed | More → Invite a Friend | OS share sheet opens with configured message/link; app does not request contact database access. | P0
AT-014 | Privacy | No learner auth | Fresh install | Use assessment, lesson, quiz, progress | No registration/login/profile is required. | P0
AT-015 | Content | Theological text integrity | Approved CMS content exists | Publish and open mobile | Displayed text matches approved content except intentional typography/layout transformations. | P0

## Scope & Future
Item | Classification | Reason / Boundary | Handling
Full KJV Bible | IN SCOPE – agreed after proposal | Supporting Bible feature; required verses remain inline in lessons. | Implement basic reader/navigation and structured lesson linking.
Full Strong’s Concordance / Greek-Hebrew engine | OUT OF SCOPE | Would create a substantial Bible-study subsystem beyond curated word studies. | Use CMS-entered curated word-study data only.
Interlinear Bible | OUT OF SCOPE | Not included in proposal/CMS decisions. | Separate scope if requested.
Learner notes/journal | OUT OF SCOPE | Client lesson instructions can ask learners to journal, but app note-taking adds persistence/editor UX. | Use Reflection/Study Activity prompts only.
Bible highlighting/annotation | OUT OF SCOPE | Large additional reader/persistence feature. | Do not implement in base scope.
Cloud learner accounts / sync | OUT OF SCOPE | Proposal explicitly uses no login and device-local progress. | Separate future module.
Arbitrary visual graph/mind-map editor | OUT OF SCOPE | Too broad; future Bible & Prophecy Connections was excluded. | Use Scripture Connection / Prophecy Equivalence predefined components.
Master Prophecy Timeline | FUTURE – OUT OF SCOPE | Explicit future expansion in proposal. | Lesson-specific timelines only in base scope.
Intelligent related-study recommendations | FUTURE – OUT OF SCOPE | Explicit future expansion in proposal. | Manual Continue Exploring links are acceptable.
AI Prophecy Assistant | FUTURE – OUT OF SCOPE | Explicit future expansion in proposal. | Separate future scope.
Custom animation production | OUTSIDE BASE COST | Proposal excludes production cost; integration is included. | Discuss/approve any additional production cost before work.
New custom interactive mechanism | CHANGE REQUEST | Standard CMS components are included; new mechanisms may require development. | Estimate and obtain approval before implementation.
Free-form no-code page builder | OUT OF SCOPE | CMS should use reusable controlled lesson components. | Use structured Lesson Builder.
Google-Docs-style collaborative editing | OUT OF SCOPE | Not required by proposal. | Basic workflow/revisions only if implemented.
GIS / Google Maps-like map editor | OUT OF SCOPE | Maps are educational visual assets, not mapping product. | Use static map/diagram + optional hotspots.
Note on A1: OpenAI: Source basis: Prophetic Destinations project proposal provided by user, plus subsequent agreed product/CMS decisions in this conversation.

## Milestones
Milestone | Primary Deliverable | Feature Groups | Target Phase
Milestone 1 | Working mobile app with learning-level selection, optional assessment, B/I/A navigation and first functional lesson flow. | APP-001–015; initial LESS-001 | Development Month 1
Milestone 2 | Working interactive lesson framework supporting Scripture, explanations, images/visuals, historical evidence, maps/timelines, animation integration and end-of-lesson quiz. | LESS; BLK; QUIZ mobile | Development Months 1–2
Milestone 3 | Functional Admin CMS integrated with mobile app for levels, courses, lessons, supported content, media, historical evidence, quizzes, ordering and publishing. | CMS; PUB; Bible picker | Development Month 2
Milestone 4 | Completed app with local progress/resume, automatic offline lesson availability, Invite a Friend, full KJV Bible (agreed addition), scoped functionality, alpha/beta fixes and production-ready submission. | PROG; OFF; SHR; BIB; MORE; NFR | Testing/Launch Month 3
3 months total
Note on A1: OpenAI: Source basis: Prophetic Destinations project proposal provided by user, plus subsequent agreed product/CMS decisions in this conversation.

## AI Prompt Guide
Prompt Section | What to Include | Example / Instruction
Role / Context | State app surface and component being implemented. | You are implementing the Prophetic Destinations React Native mobile lesson renderer.
Feature IDs | Reference exact IDs from Feature Register. | Implement LESS-001, LESS-002 and BLK-004.
Behavior | Copy the Requirement / Behavior and Acceptance Criteria. | Do not infer extra product behavior beyond the feature row.
Data contract | Use Data Model entity/fields and specify sample payload. | LessonBlock.type=scripture_passage; payload contains structured book/chapter/start/end.
Level rules | Always state B/I/A filtering and variant behavior when relevant. | Render block only when currentLevel is included in block.levels.
Offline rules | State whether data must work from cache/local storage. | Lesson content/assets must render after successful prior cache without network.
Mobile UX | Require portrait-first responsive UI and avoid desktop table assumptions. | Prophecy Comparison must stack into cards on narrow phones.
Scope guard | Explicitly state what NOT to build. | Do not add user notes, auth, cloud sync or Strong’s search.
Error states | Ask for loading, empty, invalid-content and offline failure handling. | Unknown block type should fail gracefully and log; it must not crash lesson.
Tests | Ask for unit/component/integration tests mapped to Acceptance Tests. | Cover AT-003 level filtering and AT-006 offline lesson behavior.
Content integrity | Treat theological text as data, not something the AI should rewrite. | Render CMS-approved copy exactly; do not paraphrase theology in code fixtures.
Definition of done | Include build, tests, lint/type checks, accessibility and no regression to existing blocks. | Return changed files, migration/schema changes, tests and manual verification steps.